## Slide 1: GEFS v12 relevant info GEFS v12 coordination google drive (link)
Updated on 7/30/19

## Slide 2: High Level Timeline (dates as of 9/12/19, 2/26/20)
Freeze GEFS-Atmosphere configuration for reanalysis/reforecast - Q1FY19
Freeze GEFS-Atmosphere configuration for retrospectives - Q3FY19
Freeze GEFS-Wave configuration/code for retrospectives - Q4FY19
Freeze GEFS-Aerosols configuration/code - Q4FY19 → Q2FY20
Produce 20 years reanalysis datasets (ESRL/PSD): Q3FY18 - Q4FY19 → Q3FY18 - Q1FY20
Produce 30 years reforecast extended to 35 days: Q1FY19 - Q1FY20
Produce 2-3 years retrospectives for atmosphere: Q3FY19 - Q2FY20
Produce one year retrospectives for wave ensemble: Q4FY19 - Q2FY20
Produce one year retrospectives for aerosol: Q1FY20 - Q2FY20
Freese all components code (including workflow and post) for final I&T and EE2 compliance - 4/1/20
EE2 process and coordination with NCO: Q4FY19 - Q4FY20
Deliver PNS to HQ: PNS1 (12/19), PNS2 (04/20), PNS3 (6/20), SCN (30 days before )
Field evaluation for all components: Q2FY20 (03/02/20 - 03/16/20) → 3/2/20 - 4/10/20
Science OD brief on or before 5/15/20
Deliver final package to NCO: Q3FY20; May 2020 → 04/17/20 → 05/15/20 (Tentative)
Transition to Operations Q4FY20 (Aug 26, 2020) → 09/07/20 (Tentative)

## Slide 3: Project plans related to GEFS v12
DRAFT GEFS v12 project plan and charter (link)
GEFS v12 latest Gantt chart (link)
GEFS v12 retrospective plan (link)
GEFS v12 reforecast plan (link)
GEFS v12 field evaluation plan (link)
Wave Ensemble development/evaluation plan (link)
Aerosol evaluation plan (link)
Latest SIP document (link)
GEFS V12 test plan on Dell 3.5 (link)
GEFS v12 SCN draft (link)
Published NWS PNSs (link)

## Slide 4: GEFS v12 related info
EMC/NCO kick-off meeting - 9/12/19 (link)
Products retirement list (link)
Downstream products validation (link)
Model dependency spreadsheet (link)
NWS notification: PNS, SCN,... (link)

## Slide 5: GEFS v12 related V&V information
GEFS-ops verification page (link)
GEFS v12-retrospective verification page (link)
GEFS v12-retrospective monitor system page (link)
Integrated GEFS Official Evaluation page (link)
EE2 document (link)
Example of GEFS v12 retro case study (link)

## Slide 6: Quad charts related to GEFS v12
Global Ensemble Dev quad (link)
GEFS v12 T2O quad (link)
Wave Modeling Dev quad (link)
Air Quality Modeling Dev quad (link)
Verification and Validation quad (link)
Post Processing & Products quad (link)
Model Evaluation quad (link)

## Slide 7: GEFS v12 R&R
Component | Manager | Lead | Developers (based on redmine tasks)
Overall management | Vijay | Farida | 
Atmospheric ensemble | Vijay | Yuejian/Dingchen | 
Wave Ensemble | Vijay | Henrique | Henrique, Roberto
Aerosols/Chemistry | Vijay | Jeff | 
V&V | Jason |  | Binbin, Yan Luo, Jiayi, Alicia, Deanna, Partha
Model evaluation | Jason | Geoff | Alicia
Post Processing & Products | Jason | Hui-ya | Wen Meng (Atm & Aerosol), Bhavani (Wave)
Infrastructure | Arun | Lin Gan | ?? (workflow), Lin (EE2)

## Slide 8: GEFS v12 R&R for V&V activities (FINAL)
Activity | Lead | Developers | Notes | Branch
Integrated GEFS field evaluation | Geoff Manikin | Alicia Bentley | Field evaluation | VPPPGB/Jason
Develop GEFS evaluation plan for atmospheric week 1 | Geoff Manikin | Alicia Bentley |  | VPPPGB/Jason
Develop GEFS evaluation plan for atmospheric week 2-4 | CPC |  |  | VPPPGB/Jason Vijay/MDAB
GEFS test plan and execution | Yuejian |  | Need to coordinate with Wave and NGAC teams | MDAB/Vijay
Execute verification package | BinBin Zhou | BinBin Zhou, Yan Luo, Alicia Bentley |  | VPPPGB/Jason
Develop verification tools/metrics for week 1 | BinBin Zhou | BinBin Zhou, Yan Luo, Jiayi Peng, Alicia Bentley | METplus and VSDB Is METplus ready/validated? | VPPPGB/Jason
Develop verification tools/metrics for week 2-4 | CPC |  |  | VPPPGB/Jason Vijay/MDAB
Evaluation plan for wave ensemble | Henrique |  | Share it with the GEFS team | MDAB/Vijay
Wave verification tools and execution | Deanna Spindler | Todd Spindler, Deanna Spindler | Python3 | VPPPGB/Jason
Evaluation plan for NGAC | Jeff McQueen |  | Share it with the GEFS team | MDAB/Vijay
NGAC verification tools and execution | Jeff McQueen | Jeff McQueen and Partha | METplus (need to be validated against VSDB) | MDAB/Vijay