## FV3Chem timeline
TASK | Responsible | Start Date | End date | ISSUES (Click link) | STATUS
8/21: WCOSS down 8/22: machine switch, WCOSS up Real-time run at GSD still using V0.8.7 8/26: EMC Dell R-T V0.8.7 runs close to caught up 8/27: EMC (8.7) and GSD (8.8) runs evaluatinf for July-Aug 9/3: Updated gridstat plots for V8.7, V8.8 w/ Fengsha
Test inline EDMF PBL tracer transport (v0.8.8) | GSD | 2019-08-21 | 2019-08-28 |  | 8/26: GSD runs thru 824. EMC evaluation of V8.8 ongoing 9/3: V8.8 predictions w/ Unspec. P25 added to AOD has bug 9/3: EMC regression testing started 9/10: EMC regression tests completed on all computers...code delivered COMPLETE
Perform wet scavenging/CEDS sensitivity tests - Includes runs and verif for July-Aug 2019 - includes recommended opt. config* | GSD/CSD/EMC | 2019-09-03 | Sept. 16 |  | 8/28: ARL began tuning exp for dust. Need Apr GBx data 8/27: GSD found issues with GBx smoke emissions. OC/BC much lower than PM2.5. Rec. update to UPP AOD calc. 9/3: EMC UPP has bug for T AOD calculation 9.4: GSD reran V8.8 with updated wet scavenging coef for shallow convection only. EMC evaluating 9/10: GSD running 3 V8.8 tests - wet scav. for shallow cv only, - wet scav for all cv but only OC, - full wet scav 9/13: preliminary eval vs GEOS-5 complete 9/24: Eval of EMC V8.8 runs started 10/15: complete
Perform Fengsha dust Z0/alpha coef. tests - Includes runs and verif for July 2019 - includes recommended opt. config* | ARL (Baker) | Sept. 3 | Sept. 16 | April GBBEPx files not avail, will use GFAS fires ? | 9/4: ARL provided updated threshold velocities for Fengsha 9/24: EMC and GSD using latest version of Fengsha for r-t runs 10/15: complete except for April.
Complete final V1.0.x configuration retros * C96 ATOM-1, C384 Summer 2019 eval * Rough system documentation outline * vertical profile eval ----> Eval plan link | GSD/CSD/ARL/EMC | Sept. 16 | 2020-02-07 |  | 10/15 July 5- Sept. 26, 2019 evaluation completed. - African smoke still high compared to ICAP but better than NGAC V2. - Oct. 13 canada fire, transport too far, plume rise-FRP prob ? - IC difference betw dell and hera runs being investigated - FIXED 10/28: Request to NESDIS to help evaluate BC fire problem with FRP
FIX RESTART CAPABILTY, Deliver final GSDChem source code to master, ----> Code history link | GSD/R. Montuoro |  | 2019-12-20 |  | 10/28: Problem with restart capability found, GSD to add needed fields for chem to restart files. Non-scientific change does not impact results.
| EIB/J. Wang | Sept. 3 | Sept. 10 |  | 9/12: COMPLETE
Merge GFS, GSDChem code to unified app | EIB/ J. Meixner | Sept. 11 | 2020-01-24 |  | 9/24: awaiting Wave configuraton freeze
Transition & test V1.0 code/config on Dell (regression, case) w/ dust geog. threshold velocity updates | Li Pan | Sept. 16 | 2020-01-28 |  | 9/10: V0.8.8 regression test on Dell complete 9/17: V0.8.8 full run case completed using GSD/ARL recommmended scav/dust config(workflow test)
Transition and test final GEFS workflow on Dell | Lin Gan, Li Pan, Walter K. | Sept. 16 | 2020-01-01 | DELAYED UNTIL MID NOV. | 8/23: Prepchem, Init workflow (jobs, scripts, util...) complete using V0.8.7 and GEFS workflow (L. Gan). Walter/Xianwu continue to work on fcst/post parts 9/10: First version of end to end wkflow delivered to GEFS team but GFS based 9/24: wkflow delivered was GFS and not GEFS based. GEFS working on merging 10/15: Walter finishing wave wkflow and will start aerosols soon
Test unified app with completed GEFS workflow → provide app to GEFS → Warm vs cold start tests | GEFS/Li Pan | 2019-10-15 | 2020-01-10 |  | 10/15: awaiting final workflow. Li using his custom wkflow for r-t runs
Perform FV3-Chem 1 year retro: Apr .2019 ->Mar 2020 - 12/21/19: Apr-June complete w/ modis smoke - 1/21/20: July-Sept complete - 2/10/20: Oct-Dec. complete + r-t runs | Li Pan | 2019-10-21 | 2020-05-15 | Apr-June, 2019 use MODIS fires Delayed until Mid November Not enough time to complete one year
Perform on-going MET retro & RT AOD evaluation* | Partha | 2020-02-10 | 2020-05-01 | Further scaling with fire emissions necessary
Run 1 yr budget analysis comparison | Jeff | 2020-04-01 | 2020-05-01
Present evaluation to EMC CCB | Team |  | 2020-07-10
Final science documentation | GSD, Team |  | 2020-01-31
Develop web page for hosting retrospective and real-time runs and verification graphics | Perry Shafran, Partha B.,Ho-Chun | 2020-01-03 | 2020-01-31 | - Is PPVV/MEG group willing to address aerosol needs
EE2 independent user eval | Lin Gan, Li Pan | 2020-05-15 | 2020-07-15
OD brief/Deliver final system to NCO | GEFS, Li Pan |  | 2020-07-15
GEFS V12 implemented | NCO |  | 2020-12-01
*Evaluations should include at least: - one month (July 2019) AOD verification --> vs ICAP, GEOS species, MODIS/VIIRS AOD - ATOM-1 vertical profile comparisons - will build sfc PM2.5 eval over CONUS l