## Slide 1
Project Manager: Vijay Tallapragada
Leads: Fanglin Yang and Russ Treadon (EMC), Steven Earle (NCO)
Scope: Develop and incorporate new capabilities into the NCEP GFS with 13 km resolution and 127 levels, including advanced physics and DA system, including GLDAS in DA cycle, and coupling to a wave model. Additional capabilities from the NGGPS community will also be incorporated.
Expected benefits: higher model vertical resolution, extended model domain up to the mesopause, improved model physics, advanced data assimilation, improved model forecast skills.
Dependencies: testing of NOAA MP, gravity-wave drag parameterization; wave coupling, and DA upgrade; Satisfactory evaluation by stakeholders and downstream products
GDAS/GFS Version 16
Status as of September 13, 2019
Schedule
Project Information & Highlights
Risk: Insufficient computing resources and disk space for conducting adequate testing and evaluation of newly added physics schemes and data assimilation techniques; Insufficient resources for carrying out 3 years of retrospective parallel runs mandated by NHC; Projects delayed to start: in-line UPP, workflow for wave coupling, inline GLDAS. In sufficient community support for UGWP and GFDL MP.
Mitigation: reduce the scope of updates; Reduce the length of retrospective parallels; accelerate inline UPP development to run UPP inside the model.
Issues/Risks
Management Attention Required | Potential Management Attention Needed | On Target
G
Y
R
Resources
Milestones & Deliverables | Date | Status
EMC/NCO EE2 kick off meeting | Q1FY20 | planned
Freeze model code and data assimilation system | Q4FY19 | planned
Complete full retrospective/real time runs and evaluation | Q3FY20 | planned
Complete Field evaluation & conduct CCB | Q1FY21 | planned
OD Brief and deliver final system code to NCO | Q1FY21 | planned
Deliver Service Change Notice to NCO | Q1FY21 | planned
Start 30-day evaluation and IT testing | Q2FY21 | planned
Operational Implementation | Q2FY21 | planned
Staff: 3 Fed FTEs + 10 contractor FTEs; including Dev (FV3, physics, DA, post processing, V&V, and infrastructure)
Funding Source: STI/NGGPS
Compute: EMC Dev: (+100%); Parallels: (+100%); Ops: 700 nodes HWM
Archive: Parallels: 14 PB HPSS for 3-year retros; Ops: 21TB online and 3 TB HPSS per cycle
G
Y
Y
EMC | NCO | Red text indicates change from previous quarter
Y