## task tracker
Tasks | sub tasks | Developers /POC | description | current status | due date | delayed due date, and reason for change | Redmine | documents | web links
NEMSfv3gfs package |  | Jun Wang | integrate all GFS.v16 updates into NEMSfv3gfs and prepare a package for implementation | most physics upgrade has been included | 09/30/2019 done
POST & product generation
| Inline POST -- NEMSfv3gfs code developmen | Jun Wang, Wen Meng | include UPP in NEMSfv3gfs; writes out grib2 files on Gaussian grid in the horizontal and model native grid in the vertical (?) | inline post is added to model as an option. Any future post related changes need to be added to inline post (update to post lib or update to model-post interface. using inline POST in gfs.v16 is now optional. | 10/9/2019, done |  | Tickets 64518, 70016 | Arun
| survey downstream users for UPP configuration | EIB | 1). alert downstream users GFS.v16 will produce netcdf instead of nemsio files. 2). survey users to determine what fields to add to the inline POST for running downstream models/applications |  | 2019-12-01
| offline POST | Wen Meng, Hui-ya Chuang | Update UPP for post-processing outputs from the inline POST | will use inline post | 10/30/2019, OBE
| offline POST | Wen Meng, Hui-ya Chuang | Update UPP to ingest netCDF files | Wen is comparing UPP output beween post processing nemsio and netcdf files | 2019-12-15 |  | Ticket 64518
| Station time series Bufr sounding | Guang-Ping Lou | run bufr sounding offline | Working on changes that read in NetCDF data | 2019-12-15 |  | Ticket 68939
| other product update/upgrade/sunset | Hui-ya Chuang, Wen Meng, Yali Mao, and Boi Vuong | There will be major updates to WAFS products to meet next ICAO Milestone. Also continue to sunset legacy products | Yali is working on upgrading WAFS products | 2019-12-15 |  | Tickets 67213 67215 70325 | List of products to sunet for GFS V16
| strom genesis verification | Jiayi Peng | Running NHC strom genesis verification inline in GFS.v16 parallels | wait for the cerification package from Andrew Penny from NHC | 2019-12-15 |  |  | doc
| hurricane tracker | Jiayi Peng | Update the code for TC track/genesis to prevent memory issue, and to make the package be flexible to any forecast hours. |  | 2019-12-15 |  |  | doc
| Wave model POST | Bhavani Balasubramaniyan / Henrique Alves | Review of grib2 encoding according to more recent wave parameter WMO tables. Definition of new grids for AWIPS delivery. Liasing with OPC, NHC, MAG for providing NAWIPS data files on required format/resolution. |  | 2019-12-15 |  | Ticket 68931
prep & dump
| update gblevents in obsproc_prep to read model history files in netcdf format | EIB |  |  | 2019-10-30
| check all prep &dump steps for dependences on nemsio files, and change to read netcdf history files | Shelley Melchior |  | Done. Shelley confirmed only prepobs_makeprepbufr.sh calls gblevents to read model output and EIB will take care of update of glbevent | 10/30/2019, done
Verification and Validation
| METplus into GFSv16 workflow | Mallory Row | Replace VSDB verification with METplus in GFSv16 workflow | Working on decreasing the run time for METplus, currently is running much longer than VSDB | 2019-12-15 |  | yes, but due date is 12/31/19
| Wave Model component V&V | Deanna Spindler / Henrique Alves |  |  | 2019-12-15
one-way coupling to the Wave model | Transition of wave workflow to global-workflow | Henrique Alves | Transition wave component scripts from GEFS workflow to the global-workflow. Include INIT, PREP, POST (for retrospectives), PGEN and GEMPAK steps (for near-real time and T2O). | GEFS workflow has been completed for retrospectives, scripts are being ported to the global-workflow | 2019-12-15 |  | 63039
| Alongside POST (inline) | Roberto Padilla/Henrique Alves | Add capability in WW3 to write individual binary output files at the wave model output time step. Follow up with side-by-side script that convert them to grib2. Eventually crate inline post capability to write directly onto grib2 or netcdf files. | Changes to WW3 code defined. Coding to start next week. | 2019-12-15 |  | 63041
| GFS-WW3 coupling: wind on restart files | Jessica Mexiner | NEMS coupler tasks, Include winds onto WW3 restart files | Completed. Waiting to for commit to ufs-weather-model to point to this WW3 commit. Will be a part of commit after ccpp commit. | 2019-12-15
| Wave-model checkpointing capability | Henrique Alves | Modify WW3 codes to add checkpointing output file capability | Changes to WW3 code started to be planned this week. | 2019-12-15 |  | 70259
| Adding WW3 capability to interpolate input grid to curvilinear grid. | Roberto Padilla | Internal components of the WW3 grid mosaic can be curvilinear. The stand-alone code allows reading wind data to curvilinar mosaic components only by external files with wind data provided in the target grid format. Code changes are required to allow internalll interpolation to curvilinear grids. | Completed coding. Now testing using the target GFSv16 grid mosaic coniguration with two high-latitude polar stereographic grids. | 2019-12-15 |  | 63755
| Deploy operational wave model grids in NEMSfv3gfs - finalize the configuration | Henrique Alves | Adjust NEMSfv3gfs app to run target operational wave model grids | App ported successfully to Hera and Dell. Tests using fv3 c768 and target wave model grid mosaic will resume next week. | 2019-11-15 |  | 70428
| Add GEMPAK/PGEN steps | Henrique Alves | For T2O, wave GEMPAK/PGEN steps need to be addded to the global-workflow |  | 2019-12-31 |  | 70264
| Deploy new grib2 encoding for updating wave output parameters/Update AWIPS files/headers | Bhavani | grib2 output parameters are outdated relative to recent adjustments to wave product tables published by WMO. Additional validation parameters need also to be included in grib2 files. Higher resolution and parameter-name adjustment will require updates to AWIPS headers. | grib2 tables being reviewed. Taggin up with ECMWF for consistency of definitions across centers. | 2019-12-15 |  | 68931
coupling to GLDAS | GLDAS code development | Youlong Xia, Helin Wei, Jesse Meng, Rongqian Yang, George Gayno, Fanglin Yang | Coupling GLDAS to GSI to provide land stats forced by observed precipitation | GLDAS has been updated to run with Noah forced by CPC daily 0.125-deg precip product. spin-up run; Tool for converting sfc IC from tiles to Gaussian grid to run GLDAS, and from Gaussian to tiles to update sfc ICs; test and evaluation | 2019-11-30 |  |  | 08/22/19 briefing
| workflow | EIB assigned Dexin Zhang and Hang Lei | update workflow to add GLDAS to the GFS cycling system. | need to develop new JJOB/script/ush scripts, update rocoto and ecflow for cycling; add a step to recenter ENKF member sfc files to the deterministic GDAS sfc state | 2019-10-30
GFS.v16 workflow |  | Kate Friedman, Hang Lei and all developers ? | integrate, update and maintain GFS.v16 workflow package; Timing and storage management; EE2 compliance; update ecflow scripts for operation etc | current development branch is feature/gfsv16 | 2020-05-01 |  |  | timing test
DA infrasture development | [7 empty] | google doc
| GSI package integration | Russ Treadon, Cathy Thomas | integrate all DA updates into GSI and prepare a package for implementation |  | 2019-10-30 |  | 65376
| Background errors and low-res runs | Cathy Thomas, Wan-shu Wu | Compute new climatological statistics for 127 layers. Test modification of hybrid weights to relax to static B at upper parts of model. | New static B is exercised in the real-time parallel. There will be no change to the hybrid weights. | 2019-10-30 |  | 59692, 51179
| 4D IAU | Jeff Whitaker , Russ Treadon | There is currently no initialization being used in GFS v15. 4D incremental analysis update (IAU) will be used for initialization in GFS v16 | exercised in real-time parallel | 2019-10-30 |  | 41787
| LETKF | Jeff Whitaker | EnSRF replaced with LETKF for ensemble perturbation generation. LETKF allows eomg jobs to be turned off with inclusion of jacobians in netCDF diagnostic files | exercised in real-time parallel | 2019-10-30 |  | 55874
| GSI code optimization | Russ Treadon, Jim Abeles, Cory Martin, Kristen Bathmann |  |  | 2019-10-30 |  | Issue #68133 for write increment
| SKEB | Jeff Whitaker | SKEB portion of stochastic physics was not ready for GFS v15 code freeze. Reincorporate SKEB in GFS v16 | exercised in real-time parallel | 2019-10-30
| ENKF ensemble spread; sponge-layer tuning | Jeff Whitaker |  | real-time parallel uses values recommended by Jeff | 2019-10-30 |  | 51179
| Cloud Analysis | Yanqiu Zhu / Emily Liu | remove from GFS v16
| Switch to netcdf diag files | Jeff Whitaker | A namelist switch in both the GSI and EnKF can be set to generate diagnostic files in netCDF format instead of the current binary format. The netCDF format is easier to work with. | exercised in real-time parallel | 2019-10-30
| Stratospheric humidity increments | Andrew | need an update |  | 2019-10-30
| NSST update | Xu Li | use more observations, sea ice related issues fix |  | 2019-10-30 |  | https://vlab.ncep.noaa.gov/redmine/issues/69247
| TLNMC | Daryl Kleist, Wan-shu Wu | Recommendations on changes to strong constraint configuration | No changes unless additional runtime is needed | 2019-10-30 |  | 59692
| netCDF interface | Cory Martin and Jeff Whitaker | update all GSI code and utilities to ingest netCDF files | development in ProdGSI branch feature/fv3_ncio | 2019-10-30 |  | 69217 69073 68591 69325 69326 69740
| install CRTM 2.3.0 |  | update GSI to CRTM 2.3.0 |  | 2019-10-30
| install ncio module |  | netcdf wrapper to use in various applications |  | 2019-10-30
| delz increment | Cathy Thomas | pass analysis delz increment to model |  | 2019-10-30 |  | 65376 | Results
DA data upgrade
| New variational QC | Xiujuan Su Jim Purser | Replace current operational variational QC with new scheme | ready | 2019-10-30
| Hilbert Curve application | Xiujuan Su Jim Purser | Hilbert Curve application to aircraft data | testing | 2019-10-30
| add new CSR data | Haixia Liu | add CSR data from ABI_G16, AHI_Himawari8, SEVIRI_M08 | merged to DA_GFSv16 ProdGSI branch | 2019-10-30 |  | use CSR from geostationary imagers
| assimlate high peaking radiance channels | Yanqiu Zhu | assimilation AMSUA channel 14 and ATMS channel 15 |  | 2019-10-30 |  |  |  | prfv3rad
Physics upgrade | [7 empty] | new phy plan | 64-L testing
| Gravity-wave drag | Valery Yudin, Shrinivas Moorthi, Anning Cheng, Jordan Alpert, Fanglin Yang | Test and evaluting the Unified Gravity-wave phsics; Reinstate the old orographic GWD; tuning the GWD package to improve the simulatiuon of QBO; SAO and jets in the upper atmosphere |  | 2019-10-30 |  |  | ppt on QBO
| Noah MP | Helin Wei, Rongqian Yang |  | in NEMSfvgfs; used in forecast-only and cycled runs; provide spun-up land ICs for real-time and retro runs, and for forecast-only runs | 2019-10-30 |  |  | Vlab Issue
| sa-TKE-EDMF | Jongil Han |  | further tuning for marine stratus and tropical winds | 2019-10-30 |  |  | Vlab Issue
| radiation update | Yu-tai Hou and Hsin-mu Lin |  |  | 2019-10-30
| reduce cold bias in the lower to middle troposphere in winter | Ruiyu Sun | testing updated MP from GFDL (cirrus cloud effective radis); tuning PDF-based cloud fraction etc |  | 2019-10-30
| improve PBL inversion | Jongil Han and Weizhong Zheng |  |  | 2019-10-30
| canopy heat storage | Jongil Han | add code to run with Noah_MP. | tested. Improves 500-hPa ACC, but introduces cold bias the lower tropospehre | 2019-10-30
parallels
| real-time parallel | Russ Treadon and ....... | create balanced atmospheric IC and spun-up land IC for running the 127-L GFS.v16 real-time parallel | terminate 64-layer real-time parallel with all avaliable DA and model updates included; begin 127L real-time parallel from 2019082800 | Q2FY21
| forecast-only benchmark runs | all developers | to further tune the model using IFS ICs |  | 2019-10-30 |  |  |  | early benchmark test
EE2 kick off meeting |  | Fanglin Yang |  |  | 2019-12-01
MISC and low priority items
Dry mass conservation in 32-bit hydrostatic run
Update WMO OPAC aerosol climatology to more modern one for direct radiative forcing, and for computing CCN
Remove footprint of tile corners in model output
Output radar reflectivity from model instead of computing it in the UPP
Including ice analysis in GFS.v16 package
update fix/fix_gsi/prepobs_errtable.global

## new and updated products list
FV3-SAR requests: to be added to grib2 output | avaibility in gfs v15 product
CNWAT - plant canopy moisture content [possibly already available] | pgrb2b file
SOILL - soil moisture (liquid component) [possibly already available] | pgrb2b file
ICETK - sea ice thickness. [possibly already available] | pgrb2b file
SFCR - surface roughness length (over water only) | master file
F10M - log((z0+10)/z0)
FFMM/FFHH - to initialize the exchange coefficient for momentum and heat
FRICV - friction vel | master file
TPRCP - precip rate | pgrb2 file
SRFLAG - precip type flag | pgrb2 file
TISFC - sea ice skin temperature
SOTYP - soil type | flux file
VTYPE - vegetation type | VEG in flux file